## Sheet1
% COMPLETE | JOB NUMBER | JOB NAME | LOCATION | Est. Starting Qtr | FIRE ALARM BUDGET - VENDOR BID APPROVAL | LABOR ESTIMATE | MATERIAL ESTIMATE | PM ASSIGNED | AOR | VOIP OR PHONE LINE | Plans | AMOUNT LEFT ON CONTRACT | FIRE VENDOR | INSTALL PARTNER TEAM UP WITH RER | P/S OR INSTALL | NOTES | ISSUES | 1ST MILESTONE | 2ND MILESTONE | 3RD MILESTONE | 4TH MILESTONE | 5TH MILESTONE | 6TH MILESTONE | 7TH MILESTONE | ELEVATOR FINAL | PRETEST | FINAL | C/O DROP DEAD DATE | NUMBER OF UNITS | SEP CLUB HOUSE - FIRE ALARM
0.6 | N3780 | TRAILS AT TWIN LAKES | 3006 CHARLESTON RD, DURHAM |  | 0 | N/A | N/A | ED Wolfe | NO |  | No | 38362 | ENC |  | INSTALL | ENC - THEY MESSED UP THE VA JOB AND RER IS HOLDING A LOT OF MONEY, ENC IS PROCCEDING WITH LEGAL - COULD PULL OFF THIS JOB, Bill time to RER | 2 REMAINING BUIDLINGS ARE ROUGHED BUT NOT DRYWALL FINISHED | [11 empty] | 168 | NO
0.5 | G2030 | 1100 COLUMBIA | 1009 S COLUMBIA ST, CHAPEL HILL | Q2 | 55776 | 44482.82 | N/A | JON KOSER | YES | VOIP | Done |  | RER |  | INSTALL | THIS IS A TURNKEY FOR US | BUILDING NOT DRY IN | 12/16 S ROUGH - 12/23 N ROUGH IN | TRIM S 3/30/26 TRIM N 5/4/26 | [9 empty] | 59 | NO
0.5 | G2020 | HOME 2 SUITES | 2051 CENTURY DR, RALEIGH |  | 0 | N/A | N/A | BRADLEY STOWELL | YES | VOIP | No |  | SUNLAND | CIRCUIT 5 | P/S WITH VENDOR - RER INSTALL | IS NOW A P/S WITH CIRCUIT 5 INSTALLING Bill time to RER | BEHIND AND NEED ROUGH IN BEFORE END OF THIS MONTH - TOP FLOORS TO BE ROUGH IN 2 WEEKS | 9/11 - 5TH & 4TH FLOOR ROUGH IN | 9/23 3RD FLOOR ROUGH IN | 9/25 2ND FLOOR ROUGH IN | 9/26 BELOW PODIUM ROUGH IN |  |  |  | 2024-11-04 | 10/20/25 WITH SPRINKLER SYSTEM TEST | 2025-11-03 | 2025-12-12 | 120 | NO
0 | G2040 | VARSITY AT COLLEGEVIEW | 1400 CREST RD, RALEIGH |  | 474726 |  |  | JON KOSER |  |  | Yes |  | RER | CIRCUIT 5 | P/S | HASN’T STARTED - CHANGE OVER TO RER | [12 empty] | 221 | NO
0 | G2070 | GRIFFIN WESTON 2 | 1700 EVANS RD, CARY | end Q1 Q2 | 96966 | 29657.76 | 52272.5 | JON KOSER |  |  | Done |  | RER |  | P/S | HASN’T STARTED - CHANGE OVER TO RER | [12 empty] | 52 | NO
0 | G2100 | MATORO ON MADISON | 3622 SHANNON RD, DURHAM |  | 8542 |  |  | ED Wolfe |  |  | Yes |  | RER |  | INSTALL |  |  | 3/5/26 ROUGH IN | [8 empty] | 2026-06-22 | 2026-07-16 | 6 | NO
0 | G2080 | DURANT RD | RALEIGH |  | 280500 |  |  | NELSON | YES |  | Yes |  | RER |  | INSTALL | [13 empty] | 200 | YES
0 | G2090 | THE GROUNDS | 933 GATE VIEW LN, WINSTON-SALEM | End Q1 | 442980 | 174689.75 | 167612 | BRADLEY STOWELL | No |  | Done |  | RER | CIRCUIT 5 | INSTALL | [12 empty] | 2027-05-01 | 229
0 | 122600001 | Echelon at Cary | Carry |  | 221000 |  |  | Josh Silba |  |  | Yes |  | RER | [15 empty] | 185
0 | 32500028 | Waterfront Apts | Homestead, PA |  | 230000 | [5 empty] | No |  | Management | [15 empty] | 225
0 | 32500002 | Project J | Charlotte, NC |  | 99575 | N/A | N/A | Michael Fallon | Yes |  | No |  | Dimond | [15 empty] | 84
0 | 3250035 | Spacecraft North Davidson | Charlotte, NC |  | 425000 |  |  | Brandon Ellis |  |  | Yes |  | RER | [15 empty] | 371
0 |  | 56 State Street Hotel Project | Charleston, SC |  | 129200 | [5 empty] | No |  | Management | [15 empty] | 50
0 | 142500003 | Trinity Lane Family Apartments | Nashville, TN |  | 336867 | [5 empty] | No |  | Management | [15 empty] | 233
| Total's |  |  |  | 2801132 | 248830.33 | 219884.5